## Sheet1
Task | Risk | Solution | Likelihood | Severity
Requirements | Don’t know if all requirements are achievable before deadlines. | Adding additional implementation phase for advanced tasks | 1 | 1
Character Creation | Model doesn’t fit the purpose of original design. | More research into the models to get a better model.(Unknown solution) | 1 | 1
Enemies | Damage equation is unbalanced. | Test then balance. | 1 | 1
Sounds & Music | Plays incorrect sound/SFX. | Test. | 1 | 1
Score | Doesn’t save correctly. | Test. | 1 | 1
Skybox | Textures too big. | Compress and test different versions. (Unknown solution) | 1 | 2
Dialog boxes | Font size too big/small. | Test. (Unknown solution) | 1 | 1
Currency | Money balancing. | Black box test then balance. | 1 | 1
User stories | Missed some stories, due to lack of communication with target audience. | Collect more information from users, clients, stakeholders and programmers. | 2 | 1
Testing plan | Will not fully cover everything to be tested in the final release. | Ensure full testing is completed at the end via adequate time management. | 2 | 3
Lighting | Graphical errors. | Unknown solution. | 2 | 3
Character Creation | Controls don’t work correctly. | Test. | 2 | 1
Enemies | AI is too easy/hard to play against. | Test then balance skill level. | 2 | 1
Asteroids | Algorithm procedurally spawns them incorrectly. | Test. | 2 | 3
Settings | Changing screen size might stretch images. | Test. | 2 | 3
Settings | Sound/SFX controls work incorrectly. | Test. (Unknown solution) | 2 | 3
Textures | Don’t load correctly. | Test. (Unknown solution) | 2 | 2
Dialog boxes | Alignment incorrect. | Test. (Unknown solution) | 2 | 2
Fonts | Fonts pixilated. | Get font letter sizes, then set the container size to be the same size as all of the letters combined. (Unknown solution) | 2 | 1
Flow diagrams | The flow of each chart could be incorrect as our knowledge base of DirectX is limited. | Extensive research into unknown areas e.g. labs, internet and books. | 3 | 1
WBS | Unknown amount of workload and time needed to complete each task. | Research into how to estimate, different task workloads and time management estimations. | 3 | 1
Gantt chart | Relies heavily on WBS and user stories to be correct. | Research into how to estimate, different task workloads and time management estimations. | 3 | 1
Menu setup | Buttons don’t perform correctly. | Test. | 3 | 1
Cameras | Loads every object within the game, leading to slow performance. | Implement code that only allows objects in view to be rendered. (Unknown solution) | 3 | 3
Lighting | No knowledge base. | Research from labs, internet and books.(Unknown solution) | 3 | 3
Character Creation | Collision detection. | Test. | 3 | 2
Enemies | Collision. | Test. | 3 | 2
Asteroids | Collision detection. | Test. | 3 | 3
Sounds & Music | Pauses game. | Set up threads correctly. | 3 | 2
Shadow Mapping | Incorrect shadow placement. | Test. (Unknown solution) | 3 | 1
Shadow Mapping | No knowledge base. | Research from labs, internet and books. (Unknown solution) | 3 | 2
Advanced Shaders | No knowledge base. | Research from labs, internet and books. (Unknown solution) | 3 | 1
Textures | Bump maps don’t work. | Test. (Unknown solution) | 3 | 1